## Slide 1: The Evil Triangle A Constantly Rotating Target
Tom Sloper 탐 슬로퍼

## Slide 2: Background
Started in design before becoming a producer
Atari Corp. – Director of Product Development, 1986-87
  Responsible for 35 external projects
  Expected to start up 35 more
  Impossible for one person – released 20 SKUs
  “Cheap” and “fast” were everything at Atari Corp.
  “Good” never came up
  Learned how to get things done

## Slide 3: Activision, 1988-2000
Worked on 120 external projects
And 20 internal projects
My reputation, 1988-1989: “a hell of an executor”
Japan, 1990
My rep, post-1991: “the Shanghai guru”
Trained 6 up-and-coming producers
5 awards

## Slide 4: More Recently
Mastiff Games, 2005
  Top Gun for Nintendo DS
Yahoo! Games, 2006
  5 games for IPTV (uVerse)
Naked Sky Entertainment, 2009
  Star Trek D·A·C for XBLA
University of Southern California (USC) – http://www.itp.usc.edu
  Designing & Producing Video Games
  Video Game Quality Assurance
  Game Startups Workshop

## Slide 5: The Evil Triangle
Also called “The Impossible Triangle”

## Slide 6: The Evil Triangle
The classic wisdom holds that a project cannot be cheap and fast and good; that it can only achieve two of the three.
Whether or not you believe in the Evil Triangle, you have to constantly monitor the project, and reassess your progress, so that you know where to put the most focus for the next sprint.

## Slide 7: The Evil Triangle
And even if you do believe that you can have only two points of the triangle, you never have to entirely give up on the third.
A key to achieving maximum results is to remember that "good" is a multi-pointed shape in its own right.

## Slide 8: Let’s define terms
"Fast" – Time (within planned schedule)
"Cheap" – Cost (within planned budget)
"Good" – Much more complicated to define (so we’ll start there)
"Stakeholders“ – party with vested interest
  Primary: publisher, IP owner, platform holder (and developer, if developer owns IP)
  Secondary: developer, retailer, end user

## Slide 9: QUALITY (“Good”)
Time and money are easily quantified; but “quality” is subjective.
Different people have different ideas of quality.
Quality – the “good” corner of the triangle – has multiple corners of its own. Quality can rightly be considered to consist of:
  Looks (visual quality, audio quality)
  Functionality (features, usability) (and no bugs)
  Length / depth / complexity (levels, world size, options, story – in other words: content)
  Fun

## Slide 10: Q1: LOOKS
What affects visual & audio quality
  Talent and experience can reliably produce visual/audio quality
  Time can produce quality; rushed work looks rushed
What visual quality affects in a project
  Should not cause a significant delay
  Can add to cost, but usually the major cost is in the programming
Cutting visual quality looks bad; no good reason to ever sacrifice here

## Slide 11: Q2: FEATURES
What affects functionality/usability quality
  Talent, imagination
  Competitive drive (comparing to competitive products)
  Time, and the drive to constantly improve (change requests; “feature creep”)
What functional quality affects in a project
  Time (more features take more time to implement and test)
  Cost (more personnel, more time mean higher cost)

## Slide 12: Q3: LENGTH / DEPTH
What affects game length/depth: content
  Levels, worlds, areas
  Story, characters, missions/puzzles
What game length/depth affects in a project
  Art/animation time and cost
  Audio (voice-overs, sound effects) time and cost
  Programming time and cost
  Quality Assurance testing time and cost

## Slide 13: Q4: FUN
THE MOST IMPORTANT QUALITY!
What affects fun
  Talented design (can cost more)
  Iterative design (takes more time)
  Play testing (adds to time and cost)
What fun affects in a project
  Effect on team morale
  Effect on overall sales

## Slide 14: Q4: FUN
But fun does not require more features, complexity, fancy animation, expensive voice acting talent
We often forget the value of simplicity
  ‘Tis a gift to be simple
  Simplicity can be elegant; “less is more”
  But there’s always intense pressure to add more (“feature creep”)

## Slide 15: TIME
What affects time (man-hours)
  Experience: inverse relationship with time
    Experienced team
      Experience with the technology
      Experience with the genre
      Experience with the platform
    Experienced team management
    Experienced project management
    Experienced publisher management
  Quality
    Features, more so than assets
    Change requests

## Slide 16: TIME
What more time affects
  Quality. The more time, the better the product (up to a point) – the more polish
  Cost. The more man-hours, the greater the cost
  Features. When there is time: natural inclination to add features (“feature creep” danger)
  Length / Depth. Time permits the creation of more content

## Slide 17: COST
What affects cost
  Time (man-hours)
    Features cost money
      Programming costs money
      Testing costs money
  Quality
    Experienced talent costs money
  Head count
    Overhead costs
    Head count quandary: the mythical man-month (MMM)

## Slide 18: COST
What more money affects in a project
  Quality. More money means higher quality
    Experienced talent
    And more asset creation time or talented personnel*
  More money means you can have more features
    More programming time (or head count – *subject to the MMM rule)
    More testing time (or testers*)

## Slide 19: PRIORITIZING the TRIANGLE
Rolling Stones: “You can’t always get what you want.”
If you truly can’t have all three, which two are most important (at the moment) for your stakeholders?
Unless it’s a triple-A game, most likely the schedule and budget cannot be lengthened; and they may even be shortened!
So “good” may have to give somewhere. But where?
  Functionality (features, usability)?
  Length / depth / complexity (levels, world size, options)?
  Looks (visual quality)?
  Fun?

## Slide 20: “Fast”
When fast is paramount
  Low-cost, and/or small-scale projects
  Time-sensitive projects
    Christmas releases
    Movie IP release date
When speed is expendable: AAA games
Examples (next slides)
  Top Gun DS
  Star Trek D·A·C

## Slide 21: Top Gun DS
Mastiff’s Head Woof, Bill Swartz, needed schedule shortened
Fun was not sacrificed
Visual quality was not sacrificed
Audio was done on the cheap, though

## Slide 22: Star Trek D·A·C
Producer Ben Hoyt did not believe in the Evil Triangle
Did not sacrifice fun
Did not sacrifice visual quality
Two major features had to be cut, though

## Slide 23: “Cheap”
When budget is paramount:
  Market economics (low-price product)
    XBLA
    iPhone
  Publisher unwilling/unable to spend
When money is no object: AAA games
Budget examples
    Star Trek D·A·C
    Yahoo! Games IPTV projects
    Shanghai: Second Dynasty (overspent / market shift)

## Slide 24: “Good”
When good is paramount: AAA games
When [some aspect of] quality is flexible
  Usual cuts: features, length/complexity
  Rare to sacrifice visual quality
  Fun is never expendable
Example: when “good” is paramount
  L.A. Noire (Team Biondi / Rockstar)
    8 years, and at least $50M
    Legal troubles; perpetual crunch; money probs; closure
    Money and time do not guarantee happy ending

## Slide 25: The upshot
Sometimes the bosses absolutely refuse to allot any more money (game must be "cheap"). Unless the game can’t be finished without spending more.
Often, the publisher has a crying need for the product to ship on time, or even before ("fast"). But we’ve all seen product dates slip.
And the stakeholders look bad if the game is not fun or is poor quality (it has to be "good").

## Slide 26: The upshot
With a AAA game, there is no evil triangle problem. You can have a big budget and a long schedule, because the sharpest point of the triangle must be the game's quality.
But for the rest of us, the triangle usually is a problem... Or is it? It doesn’t have to be!
Since "good" encompasses features, content, fun, and looks, there's a lot of room for tradeoffs – without sacrificing much quality.

## Slide 27: “Good” is Not a Triangle Point
“Good” is a 4-pointed star in its own right
So that’s where you can make your quality adjustments
Fun must never be sacrificed,
And looks should not be sacrificed.
But features can be reduced,
And content can be shortened.

## Slide 28: The upshot
The old saying isn’t true.
It isn’t even really a triangle.
It isn’t impossible.
And it isn’t evil.

## Slide 29: Thanks for listening! Questions?
탐 슬로퍼
Tom Sloper
Sloperama Productions
tom@sloperama.com
1-310-344-7873
Los Angeles, CA, USA
www.sloperama.com/business.html